## Project Schedule
PROJECT SCHEDULE TEMPLATE
STOCK PRICE DASHBOARD | INSHAAL, BORIS
PROJECT DELIVERABLE: Fully functional data analysis system with Streamlit UI, automated testing, final report, and presentation slide materials.
Scope: Web-based application that retrieves and visualizes real-time stock market data, allowing users to search for ticket symbols, view price history, and display interactive charts for analysis
START DATE | END DATE | OVERALL PROGRESS
2025-09-19 | 2025-12-14 | 60%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Functional Core System Architecture | Boris | 2025-10-19 | 2025-10-20 | 2 | Complete | Repo setup and config complete
Leadership Rotation | Inshaal | 2025-10-19 | 2025-10-19 | 1 | Complete | Leadership documented (Boris)
Status Report (Tuesday Check-in) | Boris | 2025-10-19 | 2025-10-21 | 3 | Complete | Check-in complete
Peer Review Presentation | Both | 2025-10-24 | 2025-10-24 | 1 | Complete | Presented progress and received feedback
Core features completed | Both | 2025-10-25 | 2025-10-27 | 3 | Complete | fetch_data.py, analyze.py, plot.py, main.py done
Testing and UI Work | Inshaal | 2025-10-29 | 2025-10-31 | 3 | Complete | Pytest files and streamlit UI draft
Integration & Refinement | Boris | 2025-10-31 | 2025-11-06 | 7 | Not complete | Backend connected and debugging UI issues
Update Test Scripts | Inshaal | 2025-11-02 | 2025-11-06 | 5 | Not complete | Verify outputs before report
Final Report Writing | Both | 2025-11-09 | 2025-11-15 | 6 | Not Started | Add screenshots and explanations
Presentation Slides | Both | 2025-11-16 | 2025-11-21 | 5 | Not Started | Include demo video and summary
Final Submission | Both | 2025-11-22 | 2025-11-23 | 2 | Not Started | Submit Github Repo + slides